## Sheet1
PLAN FOR PRODUCT
Week | Functinality | Back-end | Front-end | COST FOR Deployment
1 | Login /Logout |  |  | https://www.digitalocean.com/pricing/#general-purpose-droplets
For Freelancer
For Client (Who can post Job)
Test a login logout
Viwe Redirect to the freelacer
View redirect to the Client
Ensure that client can se freelancer
Ensure that Freelancer can see Clientpost
2 | Freelancer can send request to client
Client can approve a request of freelancer
Ensure Notification send to client
ensure notification send to Freelancer
Can intiate a chate between two people
Post Will disapear by client
Connection ensurence to Freelancer
3 | Test a Connection and notification functinality
Start Working On Chet Fuctionality
Working On forms For job Post ( for client)
Working on connections pages
Working on Page rendering to User
Working on close account and password updates
Working On Real time message functionality
4 | Teasting all functinality
Update remaining functinality
If any data or missing functinality will add